## short term
Task	Description	Recorded on
Encrypt the data in Secrets		05/03/21
Try to optimize the recovery of the K8S cluster after Vms restart.	Problem: Citus coordinator tries to start but worker 2 is down because of stateful set definition → recovers after several pod restarts ~= 5-10, which means a couple of minutes ~= 10) → probably will ask Marcos from Citus	17/3
Use external storage for the persistent volumes / Reasons: / Local cannot be used from other pods (ok for our case) / Recovery after node failure (apply Citus shards replication)	Already done this: https://docs.microsoft.com/en-us/azure/aks/azure-files-volume / Problem: The pod cannot chmod inside the file share	17/3
Citus coordinator with control plane on the same node?	probably will ask Marcos from Citus	17/3
Python access Azure	See python issue https://docs.microsoft.com/en-us/azure/developer/python/configure-local-development-environment?tabs=cmd	17/3

make SET citus.shard_replication_factor=2; permanent

## Questions
Citus coordinator with control plane on the same node? → probably will ask Marcos from Citus

## Budget
18/3	13.62