## Sheet1
Week	Tasks performed
15-21/2	Automatic cluster creation in Azure with simple bash script. / Files:automaticClusterDeployment/deployCluster.sh and installMobilityDB.sh
22-28/2	Started studying Kubernetes. / Made a first deployment of MobilityDB + Citus + Kubernetes in Azure (1 master, 1 slave) by following this link: / https://severalnines.com/database-blog/using-kubernetes-deploy-postgresql / Didn’t configure/checking Citus networking. / Files: *.yaml under KubernetesDeployment/
1/3-7/3	Finished Kubernetes Basic Tutorials / Worker for Russian PGCONF for 2 days / Deployed MobilityDB+Citus in K8S / Files: *.yaml under KubernetesDeployment/
8/3-14/3	Made several improvements to K8S Architecture / Create Architecture diagram using creately / Run pg_conf database and queries in K8S deployment / Automate the deployment process / Create docker image with latest MobilityDB and Citus 10.0 and deployed in the K8S cluster / Files: automaticClusterDeployment/KubernetesCluster/*.sh / Question for next meeting: / 1)How to handle the issue of turning off the Citus cluster (problem: Citus coord tries to start but worker 2 is down because of stateful set definition → recovers after several pod restarts ~= 5-10, which means a couple of minutes ~= 10) → probably will ask Marcos from Citus / 2)Should we use external storage for the persistent volumes → yes, try to deploy it with external disks / Local cannot be used from other pods (ok for our case) / Recovery after node failure (apply Citus shards replication) / 3)Citus coordinator with control plane on the same node? → probably will ask Marcos from Citus / 4)See python issue https://docs.microsoft.com/en-us/azure/developer/python/configure-local-development-environment?tabs=cmd
15/3-21/3	Literature, mainly read the 2 reviews for auto-scaling techniques and wrote the corresponding report
22/3-28/3	Started Python implementation: / 1) Create handmade solution for scaling in/out the cluster / File: autoscaling/Azure.py, CitusCluster.py, K8sCluster.py / 2) Literature: / - K8S Heapster (default period 60 seconds, recommended > 15 seconds) / - Scalar: Scalar is a fully distributed, extensible load testing tool, implemented in Java, that can generate high request volumes using multiple coordinated nodes
29/3-4/4	Started Developing Monitoring phase: / File: autoscaling/Azure.py / Started Developing Auto-scaling Daemon: / File: autoscaling/AutoscalingDaemon.py, utils.py